## Sheet1
Work From Home Project
Start Date - 23/3/2026
Expected Date - 1/5/2026 | * working day ( 23 ) * |  | request extension may cause
End Date - 25/5/2026 |  | (27/3/26) & (6/4/26) Holiday 11 ~ 19 Thingyan
Language : Python |  | First Time Review Date : 8/4/2026
Database : MySQL |  | Second Time Review Date : 14/5/2026 & 15/5/2026
Library : CustsomTkinter , Tkinter |  | Final Review Date : 25/5/2026
Platform : Window App
Name | Assign |  |  | Review | Next Review(2026/05/14) | Final What We Fixed & Unfinish (20256/05/22)
Win Thuzar Aung | Admin ( User Registration ) |  |  | Input Validation Check , UI | -show inline error msg in Input validation check -Input * simbol in required check item -add description in Create Team -export excel -form clear -update => edit (button text change) -Set meaning file name in code -list page UI -Can Search by Batch (eg.VARCHSR=>Batch 1, 中等【intermediate】/Numeric =>1,2) | Finished -fixed inline error msg in Input validation check -added * symbol required check item -added description attribute in Team table -fixed exporting excel file -add clear button in new team creation form -changed Text of update button to "Edit" -seted meaning file name in code when click pdf button -Fixed list of all member view -Fixed Batch format Unfinish -Soft delete -Forget Password
Zin Moh Moh Win Swe | Activity All Role |  |  | Reply Or Command Box Add | Input Edit and Delete icon in Reply session. Input Search in Announcements. | -Show the latest reply in top - Set same color in Update - Added Edit & Delete in reply session - Date Filter - Added Search Function (keyword hilight) - Adjust reply box & send button
Sai Kaung Thant Phyo | WFH Schedule ( Leader & Member ) |  |  | Member Filter & Edit button WFH or Office | Show by Calendar(included WFH/Office) | 1. Implemented all requested fixes in `Leader/leader_schedule.py` and `Member/member_schedule.py`. 2. Standardized export messages and toast behavior for PDF/Excel flows. 3. Fixed inconsistent member-filter messaging in Leader Schedule (now returns a consistent “No records found for member …” result for member-specific no-match cases). 4. Updated Leader PDF export format: * Changed `Period: ... to ...` to `Date: ... ~ ...` * Adjusted spacing under title * Aligned date line with the table layout as requested. 5. Updated Leader Excel export format: * Added title row and date range row * Applied merge/alignment styling for header section. 6. Added success toast on schedule status update from Edit popup (`Schedule updated successfully!`). 7. Fixed loading-state/controls issues (controls now re-enable correctly after no-match and other early-return branches). 8. Fixed lingering `Loading schedules...` text by restoring record count after loading completes. 9. Stabilized UI refresh behavior to reduce jitter/flicker on small datasets. 10. Added performance improvement (extra enhancement): * Introduced loading-state handling and chunked rendering for large Leader Schedule datasets to keep the UI responsive and avoid “Not Responding” during month-range fetches. * Kept small dataset rendering fast to avoid unnecessary visual movement. 11. Refactored toast rendering to a persistent single-toast pattern to avoid overlapping/ghost rectangle artifacts near the top-right area. 12. Updated Member export format to align with requested style and flow: * Kept title as `My Work Schedule` * Removed `Name:` row * Kept only `Date: ... ~ ...` * Applied alignment and header formatting updates for both PDF and Excel exports. 13. Updated the sidebar menu name from `"WFH Schedule"` to `"WFH / Office Schedule"`. 14. Fixed an issue where the holiday/weekend toast message was incorrectly triggering and showing up during the initial page load. 15. Added a List/Overview view toggle button along with a new Overview Calendar feature to allow users to switch seamlessly between a structured list and a calendar layout.
Shwe Zin May | Attendance List ( Leader & Admin & Member ) |  |  | - | Montly hours(System&PDF).Input OT hours.Change Date => From-To Date. Export by Excel. Change CURRENT WORK MODE Botton color by green | -Changed date filter(From-To Date) -Added export by Excel -Added monthly hours,working hours(system,pdf,excel) -Added check-in editor -Added break_time column (system) -Updated in calculation of OT hours
Kyi Nu Aye Chan | Tracking The Employee is working or not / Project and Tasks of Leader & Member |  |  | Member Report Percentage (Daily Record) and problems | -Check when input date over in Sumit Report -Check how to update when insert 90%=>10% (error =>10%) | Finished -added test logic (input validation) in member_project.py file -changed UI style (toggle input and edit boxx) in leader_project.py file -Fiexed UI style in task_manager.py file
Ei Khine Moe | Daily Report |  |  | report review from leader filter by member / Daily,Weekly,Monthly Report | Daily Report (Admin). Input count of members not submitted the report. Change form design by Title, Today, Tommorow, Remark boxs. Update Clear and Export Botton's right border. Change Hrs=>Hours | -Added admin daily report - Added input count of memebers not submitted and, submitted and show the list of them on admin and leader side. - Added excel format export. - Changed from the Spent Time logic to the real Daily Report logic where user can input today's works and tomorrow's work sechedule and inform some issues and any other information. - Fixed the buttons and make them all the same with other members. - Added message style for error, successful, and warning messages. - Make sure that PDF and Excel Export are all good.
Min Min Phyo | Leave Management |  |  | Half Leave Morning & Afternoon Check Box and End date disable | -Can change form design,Btn,Calendar form with other form design, Btn, Calendar -Change Form design -Can not leave request in Sat and Sunday -Delete Refresh Btn -Update (leave 2.0 D) to (leave 2.0 Days) -Show by format (20 Evening to 22 Morning ) | -Leave request holiday not allowed. -Leader/Member leave days details window -Leader Reject day/Member do not submit reject leave -Button and Form Design Change
Yin Yin Kyaw | All Role Dashboard & Design / Overtime Of leader and member |  |  | Design Check / Check In Check Out Session / Overtime | -Input error msg for required check -Can request overtime by Member -If checkout is reset, there is no need to enter the checkout time | - Fixed Input Error message for required check - Added overtime request from member - New added Successful , Error message toast - Added limit 8 hour logic for both each day
Aung Thura Khant | Data Integration + Project Structure + Database |  |  | Check in Check out session / Notifications / WFH Status | - Update member ACTIVITY status When Office /WFH (error =>Not change) - check in /check out time => overtime (調整) - check in /check out edit access | - Fixed Leader and Member Dashboard Status(WFH/Office) is working up to date chaning well - New added total count in Main Dashboard (it is counting whole company employee ) - Check-in Check-Out session working well - New added notification on the Overtime Side inside Notification Badge added menu side bar noti badge and that is not connected (working seperately) - New added Leader account Tracking too and to know himself and other leader is in working in home or office - I already sent Instructions of Button Design / Size / Color and Position , Order of Buttons Filter,Clear etc.. and padding to all members of project - All Member Export & PDF format adjusted - Tracking Added to Leader too (New)